## Management Summary
| Total |  |  | Coding |  |  | Meetings |  |  | Systems Analysis |  |  | Overhead
| Budgeted | Actual | Deficit | Budgeted | Actual | Deficit | Budgeted | Actual | Deficit | Budgeted | Actual | Deficit | Budgeted | Actual | Deficit
Anne | 9500 | 11100 | -1600 | 4400 | 4200 | 200 | 1000 | 3000 | -2000 | 1100 | 1300 | -200 | 3000 | 2600 | 400
Bill | 9800 | 9900 | -100 | 4700 | 4200 | 500 | 1000 | 2600 | -1600 | 1100 | 1000 | 100 | 3000 | 2100 | 900
Chris | 11100 | 10200 | 900 | 6000 | 1800 | 4200 | 1000 | 2600 | -1600 | 1100 | 1500 | -400 | 3000 | 4300 | -1300
Dan | 13500 | 11600 | 1900 | 8400 | 4400 | 4000 | 1000 | 2600 | -1600 | 1100 | 1100 | 0 | 3000 | 3500 | -500
Eric | 13500 | 11400 | 2100 | 8400 | 4400 | 4000 | 1000 | 2600 | -1600 | 1100 | 900 | 200 | 3000 | 3500 | -500
Fran | 13500 | 11800 | 1700 | 8400 | 4400 | 4000 | 1000 | 2600 | -1600 | 1100 | 1300 | -200 | 3000 | 3500 | -500
Total | 70900 | 66000 | 4900 | 40300 | 23400 | 16900 | 6000 | 16000 | -10000 | 6600 | 7100 | -500 | 18000 | 19500 | -1500

## Gantt
| predicted time(hrs) | time spent(hrs) | Status | key | complete | this week | planned
Anne |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59
Requirements Collection | 2 | 2 | complete | key 1: complete; complete 2: complete
Repo + Git Setup | 1 | 2 | complete | this week 3: complete; planned 4: complete
Installation | 1 | 1 | complete | planned 5: complete
Music - Pre Loaded | 2 | 1 | complete | planned 6: complete
Base Sound Managment | 2 | 3 | complete | planned 7: complete; planned 8: complete; planned 9: complete
Base Sound - Obstacle Connection | 3 | 3 | complete | planned 10: complete; planned 11: complete; planned 12: complete
Testing | 4 | 4 | complete | planned 13: complete; planned 14: complete; planned 15: complete; planned 16: complete
In-Depth Frequency + Obstacle Connection (Beatmap working) | 12 | 13 | complete | planned 17: complete; planned 18: complete; planned 19: complete; planned 20: complete; planned 21: complete; planned 22: complete; planned 23: complete; planned 24: complete; planned 25: complete; planned 26: complete; planned 27: complete; planned 28: complete; planned 29: complete
Integrate With Song Menu | 2 | 1 | complete | planned 30: complete
Coin/Power-up integration | 1 | 1 | complete | planned 31: complete
Documentation | 5 | 3 | this week | planned 32: this week; planned 33: this week; planned 34: this week; planned 35: this week; planned 36: this week
Further Testing | 5 | 8 | this week | planned 37: this week; planned 38: this week; planned 39: this week; planned 40: this week; planned 41: this week; planned 42: this week; planned 43: this week; planned 44: this week
Adding Patterns and Other Requirements | 4 |  | planned | planned 45: planned; planned 46: planned; planned 47: planned; planned 48: planned
totals | 44 | 42
Bill
Requirements Collection | 2 | 3 | complete | key 1: complete; complete 2: complete; this week 3: complete
Track Design | 3 | 2 | complete | planned 4: complete; planned 5: complete
Character Design | 3 | 2 | complete | planned 6: complete; planned 7: complete
Background Design | 3 | 2 | complete | planned 8: complete; planned 9: complete
View Track Functionality | 4 | 4 | complete | planned 10: complete; planned 11: complete; planned 12: complete; planned 13: complete
View Background Functionality | 4 | 4 | complete | planned 14: complete; planned 15: complete; planned 16: complete
View Character Functionality | 4 | 3 | complete | planned 17: complete
View Obstacles Functionality | 6 | 1 | complete | planned 18: complete; planned 19: complete; planned 20: complete; planned 21: complete; planned 22: complete; planned 23: complete
Create Testing Functionality | 4 | 6 | complete | planned 24: complete; planned 25: complete; planned 26: complete; planned 27: complete; planned 28: complete; planned 29: complete; planned 30: complete; planned 31: complete; planned 32: complete; planned 33: complete; planned 34: complete; planned 35: complete; planned 36: complete; planned 37: complete; planned 38: complete
Debug Project Code | 10 | 15 | this week | planned 39: this week; planned 40: this week; planned 41: this week; planned 42: this week
Integrate With Other Components | 4 |  | planned
totals | 47 | 42
Chris
Obstacle Design | 5 | 4 | complete | key 1: complete; complete 2: complete; this week 3: complete; planned 4: complete
Obstacle Implementation | 10 | 1 | complete | planned 5: complete
Get obstacles to stick to track | 15 | 4 | complete | planned 6: complete; planned 7: complete; planned 8: complete; planned 9: complete
Get obstascles to move with track. | 15 | 5 | complete | planned 10: complete; planned 11: complete; planned 12: complete; planned 13: complete; planned 14: complete
Patterns | 5 | 2 | complete | planned 15: complete; planned 16: complete
Testing | 5 | 2 | this week | planned 17: this week; planned 18: this week
Installation | 5 |  | planned | planned 19: planned; planned 20: planned; planned 21: planned; planned 22: planned; planned 23: planned
totals | 60 | 18
Dan
HUD Layout | 5 | 5 | complete | key 1: complete; complete 2: complete; this week 3: complete; planned 4: complete; planned 5: complete
Score Control | 10 | 5 | complete | planned 6: complete; planned 7: complete; planned 8: complete; planned 9: complete; planned 10: complete
Display Score | 10 | 6 | complete | planned 11: complete; planned 12: complete; planned 13: complete; planned 14: complete; planned 15: complete; planned 16: complete
Implmentation of Mulitplier & Display | 10 | 2 | complete | planned 17: complete; planned 18: complete
Song Score Implementation & Time Display | 10 | 6 | complete | planned 19: complete; planned 20: complete; planned 21: complete; planned 22: complete; planned 23: complete; planned 24: complete
Menu Button Implementation and Display | 10 | 2 | complete | planned 25: complete; planned 26: complete
Progression Bar, Mini Map | 5 | 4 | complete | planned 27: complete; planned 28: complete; planned 29: complete; planned 30: complete
HighScore Display & Implmentation | 10 | 6 | complete | planned 31: complete; planned 32: complete; planned 33: complete; planned 34: complete; planned 35: complete; planned 36: complete
Background Enhancements & Art | 5 | 4 | complete | planned 37: complete; planned 38: complete; planned 39: complete; planned 40: complete
Character Art Enhancement | 2 | 2 | complete | planned 41: complete; planned 42: complete
Dr-BC Mode Hotkey & Undo (B, N) | 2 | 2 | this week | planned 43: this week; planned 44: this week
Track Enhancements and Art | 5 |  | planned | planned 45: planned; planned 46: planned; planned 47: planned; planned 48: planned; planned 49: planned
totals | 84 | 44
Eric (Note: Just a copy of Dan)
HUD Layout | 5 | 5 | complete | key 1: complete; complete 2: complete; this week 3: complete; planned 4: complete; planned 5: complete
Score Control | 10 | 5 | complete | planned 6: complete; planned 7: complete; planned 8: complete; planned 9: complete; planned 10: complete
Display Score | 10 | 6 | complete | planned 11: complete; planned 12: complete; planned 13: complete; planned 14: complete; planned 15: complete; planned 16: complete
Implmentation of Mulitplier & Display | 10 | 2 | complete | planned 17: complete; planned 18: complete
Song Score Implementation & Time Display | 10 | 6 | complete | planned 19: complete; planned 20: complete; planned 21: complete; planned 22: complete; planned 23: complete; planned 24: complete
Menu Button Implementation and Display | 10 | 2 | complete | planned 25: complete; planned 26: complete
Progression Bar, Mini Map | 5 | 4 | complete | planned 27: complete; planned 28: complete; planned 29: complete; planned 30: complete
HighScore Display & Implmentation | 10 | 6 | complete | planned 31: complete; planned 32: complete; planned 33: complete; planned 34: complete; planned 35: complete; planned 36: complete
Background Enhancements & Art | 5 | 4 | complete | planned 37: complete; planned 38: complete; planned 39: complete; planned 40: complete
Character Art Enhancement | 2 | 2 | complete | planned 41: complete; planned 42: complete
Dr-BC Mode Hotkey & Undo (B, N) | 2 | 2 | this week | planned 43: this week; planned 44: this week
Track Enhancements and Art | 5 |  | planned | planned 45: planned; planned 46: planned; planned 47: planned; planned 48: planned; planned 49: planned
totals | 84 | 44
Fran (Note: Just a copy of Dan
HUD Layout | 5 | 5 | complete | key 1: complete; complete 2: complete; this week 3: complete; planned 4: complete; planned 5: complete
Score Control | 10 | 5 | complete | planned 6: complete; planned 7: complete; planned 8: complete; planned 9: complete; planned 10: complete
Display Score | 10 | 6 | complete | planned 11: complete; planned 12: complete; planned 13: complete; planned 14: complete; planned 15: complete; planned 16: complete
Implmentation of Mulitplier & Display | 10 | 2 | complete | planned 17: complete; planned 18: complete
Song Score Implementation & Time Display | 10 | 6 | complete | planned 19: complete; planned 20: complete; planned 21: complete; planned 22: complete; planned 23: complete; planned 24: complete
Menu Button Implementation and Display | 10 | 2 | complete | planned 25: complete; planned 26: complete
Progression Bar, Mini Map | 5 | 4 | complete | planned 27: complete; planned 28: complete; planned 29: complete; planned 30: complete
HighScore Display & Implmentation | 10 | 6 | complete | planned 31: complete; planned 32: complete; planned 33: complete; planned 34: complete; planned 35: complete; planned 36: complete
Background Enhancements & Art | 5 | 4 | complete | planned 37: complete; planned 38: complete; planned 39: complete; planned 40: complete
Character Art Enhancement | 2 | 2 | complete | planned 41: complete; planned 42: complete
Dr-BC Mode Hotkey & Undo (B, N) | 2 | 2 | this week | planned 43: this week; planned 44: this week
Track Enhancements and Art | 5 |  | planned | planned 45: planned; planned 46: planned; planned 47: planned; planned 48: planned; planned 49: planned
totals | 84 | 44
group totals (hrs) | 235 | 146
group totals ($) | 23500 | 14600

## Team Mate Delverables
TL 1 Deliverables |  |  | TL 2 Deliverables |  |  | TL 3 Deliverables |  | TL 4 Deliverables | TL 5 Deliverables | TL 6 Deliverables
Date Due: 11/27 |  |  | Date Due: 11/27 |  |  | Date Due: 11/27 |  | Date Due: 10/23 & 10/25 | Date Due: 11/1 | Date Due: 11/6 & 11/8
By Monday 11/27: Initial Readme File in GIT |  |  | By Monday 11/27: Initial function in GIT that the MVP can call |  |  | By Monday 11/27: Submit to GIT: 2 Boundary Tests 1 Stress Test |  | By Monday 10/23: | By Wednesday 11/1@6pm: | By Monday 11/6:
[8 empty] | 1. Fully update your sections of the Gantt chart | 1: Update the gantt for what you have worked on.
2: Send me an update on what you have been working on this week.
By Wednesday 10/25:
1. Look over the coding standards in the GIT
2. Try to update your code to comply with the coding standards (to the best of your ability, BC is not expecting it to be perfect). Message me when you're done and I'll check you off.
Location: |  |  | Location: |  |  | Location: |  | Location: | Location: | Location:
Get deliverables to TL by 6pm on Date Due
Deliverable Tracker
| Abby | Bill | Carly | Dan | Eren | Fred | George
TL 1 | ü | ü | ü | ü | ü | ü | ü
TL 2 | ü | ü | ü | ü | ü | ü | ü
TL 3 | ü | ü | ü | ü | ü | ü | ü
TL 4 | ü | ü | ü | ü | ü | ü | ü
TL 5 | ü | ü | ü | ü | ü | ü | ü
TL 6 | ü | ü | ü |  | ü | ü | ü

## Meetings
| Date | Aug. 30 | Sept. 1 | Sept. 13 | Sept. 15 | Sept. 21 | Sept. 22 | Sept. 23 | Sept. 29 | Oct. 4 | Oct. 20
| Purpose | First Meeting | Ananlysis Planning | Ananlysis Integration | Ananlysis presentation practice | Initial Set-up | Initial Set-up | Initial Set-up | Initial Release | Team Lead 2 demo practice | Test Code Integrateion
| Hours | 1 | 4 | 2 | 2 | 2 | 2 | 2 | 6 | 1 | 8
Anne | 30 | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü
Bill | 26 | ü | ü | ü | ü | ü |  |  | ü | ü | ü
Chris | 26 | ü | ü | ü | ü |  | ü |  | ü | ü | ü
Dan | 26 | ü | ü | ü | ü |  |  | ü | ü | ü | ü
Eric | 26 | ü | ü | ü | ü |  |  | ü | ü | ü | ü
Fran | 26 | ü | ü | ü | ü |  |  | ü | ü | ü | ü
Total | 160 | 6 | 24 | 12 | 12 | 4 | 4 | 8 | 36 | 6 | 48
ü

## SA
| Task | Predicted(hrs) | spent(hrs) | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
Anne | Individual schedule | 2 | 2 | bar: 1 to 2
| Champion | 5 | 6 | bar: 7 to 11
| Chapter 1 and 2, glossary Terms | 4 | 5 | bar: 3 to 6
| Subtotal | 11 | 13
Bill | Individual schedule | 2 | 3 | bar: 1 to 2
| Champion | 5 | 2 | bar: 7 to 11
| Chapter 3 and 4, glossary Terms | 4 | 5 | bar: 3 to 6
| Subtotal | 11 | 10
Chris | Individual schedule | 1 | 1 | bar: 1
| Champion | 5 | 8 | bar: 2 to 6
| Merge schedules on google docs | 2 | 2 | bar: 7 to 8
| Standardize formating | 1 | 1 | bar: 9
| Assemble SA Powerpoint | 2 | 3 | bar: 10 to 11
| Subtotal | 11 | 15
Dan | Individual schedule | 2 | 2 | bar: 1 to 2
| Champion | 5 | 4 | bar: 7 to 11
| Chapter 5 and 6, glossary Terms | 4 | 5 | bar: 3 to 6
| Subtotal | 11 | 11
Eric | Individual schedule | 2 | 2 | bar: 1 to 2
| Champion | 5 | 4 | bar: 7 to 11
| Edit Chatpers 1-3 | 4 | 3 | bar: 3 to 6
| Subtotal | 11 | 9
Fran | Individual schedule | 2 | 2 | bar: 1 to 2
| Champion | 5 | 4 | bar: 7 to 11
| Edit Chatpers 4-6 | 4 | 7 | bar: 3 to 6
| Subtotal | 11 | 13
| Total | 44 | 51
red is dependent on others

## Overhead
| Anne | Bill | Chris | Dan | Eric | Fran
Training | 10 | 6 | 27 | 9 | 9 | 9
SA Preesentation Prep | 2 | 3 | 1 | 6 | 6 | 6
Software Specialist Presnetaion Prep | 1 | 2 | 2 | 1 | 1 | 1
Team Lead Presentation Prep | 4 | 6 | 3 | 7 | 7 | 7
Oral Exam Prep | 8 | 3 | 9 | 11 | 11 | 11
Post Mortum Presentation Prep | 1 | 1 | 1 | 1 | 1 | 1
Total | 26 | 21 | 43 | 35 | 35 | 35